### PE 4. TEAM AGREEMENT

| Auditee: | Ministry of Education | Reviewed by: | Name | Rank | Date |
| --- | --- | --- | --- | --- | --- |
| Period end: | 30 June 2xx1 | Level 1 | E Solangani | Audit manager | 22 January 2xx1 |
| Prepared by: | E Tiluna | Level 2 | E Boshuma | Audit director | 25 January 2xx1 |
| Rank: | Team Leader | Level 3 | T Papandora | AAG | 30 January 2xx1 |
| Date: | 20 January 2xx1 |  |  |  |  |

ROLES AND RESPONSIBILITIES

| Working papers | Team members responsible | Insert persons’ name responsible for |  |  |  | Dates for finalisation |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Completing | 1st level review | 2nd level review | 3rd level review | Completed by | Reviewed by (1st level) |
| Pre-engagement activities |  |  |  |  |  | 20 January 2xx1 | 31 January 2xx1 |
| Code of Ethics declaration | All | E Tiluna | E Solangani | Audit director: E Boshuma | AAG: T Papandora |  |  |
| Code of Ethics conclusion |  |  |  | Audit director: E Boshuma |  |  |  |
| Competency matrix | All | E Tiluna | E Solangani | Audit director: E Boshuma | AAG: T Papandora |  |  |
| Audit engagement letter |  | E Tiluna | E Solangani | Audit director: E Boshuma | AAG: T Papandora |  |  |
| Budget v Actual hours | All | E Tiluna | E Solangani | Audit director: E Boshuma | AAG: T Papandora |  |  |
| Strategic planning |  |  |  |  |  | 15 March 2xx1 | 31 March 2xx1 |
| Planning Materiality | E Tiluna | E Tiluna | E Solangani |  |  |  |  |
| Lead schedule | E Tiluna | E Tiluna | E Solangani |  |  |  |  |
| Prior year audit matters | G Morgana M. Shonai | G Morgana | E Tiluna | E Solangani |  |  |  |
| Analytical review | E Tiluna H Monanga | E Tiluna | E Solangani |  |  |  |  |
| Review of internal audit | W Kunjaba M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Audit committee checklist | W Kunjaba M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Fraud checklist | H Monanga G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Internal control checklist IT Internal control checklist | E Tiluna G Morgana W Kunjaba H Monanga | E Tiluna | E Solangani |  |  |  |  |
| Sustainability of services checklist (going concern) | M. Shonai | M. Shonai | E Tiluna |  |  |  |  |
| Using the work of another auditor | N/a |  |  |  |  |  |  |
| Using the work of an expert | N/a |  |  |  |  |  |  |
| Risk of material misstatement on a financial statement level | E Tiluna G Morgana | E Tiluna | E Solangani | Audit director: E Boshuma |  |  |  |
| Overall Audit Strategy | E Tiluna G Morgana | E Tiluna | E Solangani | Audit director: E Boshuma | AAG: T Papandora |  |  |
| Engagement team discussion document | All | E Tiluna | E Solangani | Audit director: E Boshuma |  |  |  |
| Detailed planning and fieldwork |  |  |  |  |  | 31 August 2xx1 | 15 September 2xx1 |
| Receipts (exchequer issues and other income) |  |  |  |  |  |  |  |
| System description for audit components | H Monanga G Morgana | H Monanga | E Tiluna | E Solangani |  |  |  |
| Reliance on key controls for components | H Monanga G Morgana | H Monanga | E Tiluna | E Solangani |  |  |  |
| Audit programs | H Monanga G Morgana | H Monanga | E Tiluna | E Solangani |  |  |  |
| Sampling | H Monanga G Morgana | H Monanga | E Tiluna | E Solangani |  |  |  |
| Evidence tracking sheet | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Lead schedule on component level | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Tests of controls | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Substantive audit procedures performance | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Substantive analytical procedures | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Audit summary memorandum | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Expenditure |  |  |  |  |  |  |  |
| Supplies and consumables |  |  |  |  |  |  |  |
| System description for audit components | M Shonai W Kunjaba | M Shonai | E Tiluna | E Solangani |  |  |  |
| Reliance on key controls for components | M Shonai W Kunjaba | M Shonai | E Tiluna | E Solangani |  |  |  |
| Audit programs | M Shonai W Kunjaba | M Shonai | E Tiluna | E Solangani |  |  |  |
| Sampling | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Evidence tracking sheet | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Lead schedule on component level | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Tests of controls | M Shonai W Kunjaba | M Shonai | E Tiluna | E Solangani |  |  |  |
| Substantive audit procedures performance | M Shonai W Kunjaba | M Shonai | E Tiluna | E Solangani |  |  |  |
| Substantive analytical procedures | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Audit summary memorandum | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Personnel expenditure (Salaries paid and allowances) |  |  |  |  |  |  |  |
| System description for audit components | G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Reliance on key controls for components | G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Audit programs | G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Sampling | G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Evidence tracking sheet | G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Lead schedule on component level | G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Tests of controls | G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Substantive audit procedures performance | G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Substantive analytical procedures | G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Audit summary memorandum | G Morgana | G Morgana | E Tiluna | E Solangani |  |  |  |
| Assets (Non-current and intangible assets) |  |  |  |  |  |  |  |
| System description for audit components | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Reliance on key controls for components | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Audit programs | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Sampling | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Evidence tracking sheet | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Lead schedule on component level | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Tests of controls | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Substantive audit procedures performance | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Substantive analytical procedures | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Bank and cash |  |  |  |  |  |  |  |
| System description for audit components | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Reliance on key controls for components | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Audit programs | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Sampling | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Evidence tracking sheet | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Lead schedule on component level | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Tests of controls | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Substantive audit procedures performance | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Substantive analytical procedures | M Shonai | M Shonai | E Tiluna | E Solangani |  |  |  |
| Transfers (Revenue and current transfers) |  |  |  |  |  |  |  |
| System description for audit components | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Reliance on key controls for components | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Audit programs | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Sampling | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Evidence tracking sheet | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Lead schedule on component level | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Tests of controls | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Substantive audit procedures performance | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Substantive analytical procedures | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Liabilities (arrears of revenue) |  |  |  |  |  |  |  |
| System description for audit components | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Reliance on key controls for components | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Audit programs | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Sampling | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Evidence tracking sheet | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Lead schedule on component level | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Tests of controls | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Substantive audit procedures performance | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Substantive analytical procedures | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Audit summary memorandum | H Monanga | H Monanga | E Tiluna | E Solangani |  |  |  |
| Audit summary |  |  |  |  |  | 15 October 2xx1 | 30 October 2xx1 |
| Disclosure checklist | E Tiluna | E Tiluna | E Solangani |  |  |  |  |
| Management Representation letter | G Morgana | G Morgana | E Solangani |  |  |  |  |
| Subsequent events | G Morgana | G Morgana | E Solangani |  |  |  |  |
| Final analytical review | E Tiluna | E Tiluna | E Solangani |  |  |  |  |
| Audit differences. | G Morgana E Tiluna | E Tiluna | E Solangani | Audit director: E Boshuma |  |  |  |
| Code of ethics compliance | All | E Tiluna | E Solangani | Audit director: E Boshuma | AAG: T Papandora |  |  |
| Audit query | E Tiluna G Morgana H Monanga M Shonai | E Tiluna | E Solangani |  |  |  |  |
| Review worksheet | E Tiluna E Solangani E Boshuma |  |  |  |  |  |  |
| Audit reporting |  |  |  |  |  | 15 November 2xx1 | 30 November 2xx1 |
| Management letter | G Morgana E Tiluna | E Tiluna | E Solangani | Audit director: E Boshuma | AAG: T Papandora |  |  |
| Audit report. | E Tiluna | E Tiluna | E Solangani | Audit director: E Boshuma | AAG: T Papandora |  |  |
| Representation by audit management |  |  | E Solangani | Audit director: E Boshuma | AAG: T Papandora |  |  |
| Quality control |  |  |  |  |  | Ongoing | Ongoing |
| Quality control questionnaire | All | E Tiluna | E Solangani | Audit director: E Boshuma | AAG: T Papandora |  |  |

AGREEMENT OF TEAM MEMBERS

I, the undersigned fully understand the requirements and my responsibilities relating to the audit of Ministry of Education and Vocational Training for the year ended 2xx1.

| Name of team member | Rank/Title | Signature of team member |
| --- | --- | --- |
| E Solangani | Audit manager | E Solangani |
| E Tiluna | Auditor I | E Tiluna |
| G Morgana | Auditor I | G Morgana |
| M Shonai | Auditor II | M Shonai |
| H Monanga | Auditor II | H Monanga |
| W Kunjaba | Ass. Auditor | W Kunjaba |

Note: the Team Leader: E Tiluna is responsible for the first level review of all planning and fieldwork working papers.